## Sheet
Remediation ID | Finding ID | Finding Title | Source | Risk ID | Control ID | Application ID | Vendor ID | Severity | Privacy Impact | Business Impact | Root Cause | Corrective Action Plan | Remediation Owner | Department | Assigned Date | Due Date | Status | Priority | Evidence Required | Evidence Submitted | Retest Status | Aging Days | Overdue Flag
REM-001 | FIND-001 | Remediate Security Control Deficiency for CTRL-001 | Internal Audit / Vendor Incident | RISK-001 | CTRL-001 | APP-001 | None | Critical | Moderate | High (Compliance & Security) | Process procedural gap | Implement automated technical safeguard to enforce control CTRL-001 | Engineering Lead 1 | Software Engineering | 2026-08-02 | 2026-09-02 | Closed | High | Evidence File EVID-001 | EVID-001 Attached | Passed | 22 | No
REM-002 | FIND-002 | Remediate Security Control Deficiency for CTRL-002 | Internal Audit / Vendor Incident | RISK-002 | CTRL-002 | APP-001 | None | High | Moderate | High (Compliance & Security) | Process procedural gap | Implement automated technical safeguard to enforce control CTRL-002 | Engineering Lead 2 | Software Engineering | 2026-08-02 | 2026-09-02 | Closed | Medium | Evidence File EVID-002 | EVID-002 Attached | Passed | 22 | No
REM-003 | FIND-003 | Remediate Security Control Deficiency for CTRL-003 | Internal Audit / Vendor Incident | RISK-003 | CTRL-003 | APP-001 | None | High | Moderate | High (Compliance & Security) | Process procedural gap | Implement automated technical safeguard to enforce control CTRL-003 | Engineering Lead 3 | Software Engineering | 2026-08-02 | 2026-09-02 | Closed | Medium | Evidence File EVID-003 | EVID-003 Attached | Passed | 22 | No
REM-004 | FIND-004 | Remediate Security Control Deficiency for CTRL-004 | Internal Audit / Vendor Incident | RISK-004 | CTRL-004 | APP-001 | None | High | Moderate | High (Compliance & Security) | Process procedural gap | Implement automated technical safeguard to enforce control CTRL-004 | Engineering Lead 4 | Software Engineering | 2026-08-02 | 2026-09-02 | Closed | Medium | Evidence File EVID-004 | EVID-004 Attached | Passed | 22 | No
REM-005 | FIND-005 | Remediate Security Control Deficiency for CTRL-005 | Internal Audit / Vendor Incident | RISK-005 | CTRL-005 | APP-001 | None | High | Moderate | High (Compliance & Security) | Process procedural gap | Implement automated technical safeguard to enforce control CTRL-005 | Engineering Lead 5 | Software Engineering | 2026-08-02 | 2026-09-02 | Closed | Medium | Evidence File EVID-005 | EVID-005 Attached | Passed | 22 | No
REM-006 | FIND-006 | Remediate Security Control Deficiency for CTRL-006 | Internal Audit / Vendor Incident | RISK-006 | CTRL-006 | APP-001 | None | High | Moderate | High (Compliance & Security) | Process procedural gap | Implement automated technical safeguard to enforce control CTRL-006 | Engineering Lead 6 | Software Engineering | 2026-08-02 | 2026-09-02 | Closed | Medium | Evidence File EVID-006 | EVID-006 Attached | Passed | 22 | No
REM-007 | FIND-007 | Remediate Security Control Deficiency for CTRL-007 | Internal Audit / Vendor Incident | RISK-007 | CTRL-007 | APP-001 | None | High | Moderate | High (Compliance & Security) | Process procedural gap | Implement automated technical safeguard to enforce control CTRL-007 | Engineering Lead 7 | Software Engineering | 2026-08-02 | 2026-09-02 | Closed | Medium | Evidence File EVID-007 | EVID-007 Attached | Passed | 22 | No
REM-008 | FIND-008 | Remediate Security Control Deficiency for CTRL-008 | Internal Audit / Vendor Incident | RISK-008 | CTRL-008 | APP-001 | None | Critical | Moderate | High (Compliance & Security) | Process procedural gap | Implement automated technical safeguard to enforce control CTRL-008 | Engineering Lead 8 | Software Engineering | 2026-08-02 | 2026-09-02 | Closed | High | Evidence File EVID-008 | EVID-008 Attached | Passed | 22 | No
REM-009 | FIND-009 | Remediate Security Control Deficiency for CTRL-009 | Internal Audit / Vendor Incident | RISK-009 | CTRL-009 | APP-001 | None | High | Moderate | High (Compliance & Security) | Process procedural gap | Implement automated technical safeguard to enforce control CTRL-009 | Engineering Lead 9 | Software Engineering | 2026-08-02 | 2026-09-02 | Closed | Medium | Evidence File EVID-009 | EVID-009 Attached | Passed | 22 | No
REM-010 | FIND-010 | Remediate Security Control Deficiency for CTRL-010 | Internal Audit / Vendor Incident | RISK-010 | CTRL-010 | APP-001 | None | High | Moderate | High (Compliance & Security) | Process procedural gap | Implement automated technical safeguard to enforce control CTRL-010 | Engineering Lead 10 | Software Engineering | 2026-08-02 | 2026-09-02 | Closed | Medium | Evidence File EVID-010 | EVID-010 Attached | Passed | 22 | No
REM-011 | FIND-011 | Remediate Security Control Deficiency for CTRL-011 | Internal Audit / Vendor Incident | RISK-011 | CTRL-011 | APP-001 | None | High | Moderate | High (Compliance & Security) | Process procedural gap | Implement automated technical safeguard to enforce control CTRL-011 | Engineering Lead 11 | Software Engineering | 2026-08-02 | 2026-09-02 | Closed | Medium | Evidence File EVID-011 | EVID-011 Attached | Passed | 22 | No
REM-012 | FIND-012 | Enforce Okta SAML SSO Federation & MFA for MedReport Cloud (VEND-001) | Internal Audit / Vendor Incident | RISK-012 | CTRL-012 | APP-005 | VEND-001 | Critical | High | High (Compliance & Security) | Failure to enforce MFA policy | Migrate MedReport Cloud maintenance access to Okta SAML SSO federation with forced WebAuthn MFA and IP whitelisting. | DevOps Lead / Identity Lead | DevOps / Security | 2026-08-02 | 2026-09-02 | Closed | High | Evidence File EVID-012 | EVID-012 Attached | Passed | 18 | No
REM-013 | FIND-013 | Remediate Security Control Deficiency for CTRL-013 | Internal Audit / Vendor Incident | RISK-013 | CTRL-013 | APP-001 | None | Medium | Moderate | High (Compliance & Security) | Process procedural gap | Implement automated technical safeguard to enforce control CTRL-013 | Engineering Lead 13 | Software Engineering | 2026-08-02 | 2026-09-02 | Closed | Medium | Evidence File EVID-013 | EVID-013 Attached | Passed | 22 | No
REM-014 | FIND-014 | Remediate Security Control Deficiency for CTRL-014 | Internal Audit / Vendor Incident | RISK-014 | CTRL-014 | APP-001 | None | Medium | Moderate | High (Compliance & Security) | Process procedural gap | Implement automated technical safeguard to enforce control CTRL-014 | Engineering Lead 14 | Software Engineering | 2026-08-02 | 2026-09-02 | Closed | Medium | Evidence File EVID-014 | EVID-014 Attached | Passed | 22 | No
REM-015 | FIND-015 | Remediate Security Control Deficiency for CTRL-015 | Internal Audit / Vendor Incident | RISK-015 | CTRL-015 | APP-001 | None | Critical | Moderate | High (Compliance & Security) | Process procedural gap | Implement automated technical safeguard to enforce control CTRL-015 | Engineering Lead 15 | Software Engineering | 2026-08-02 | 2026-09-02 | Closed | High | Evidence File EVID-015 | EVID-015 Attached | Passed | 22 | No
REM-016 | FIND-016 | Remediate Security Control Deficiency for CTRL-016 | Internal Audit / Vendor Incident | RISK-016 | CTRL-016 | APP-001 | None | Medium | Moderate | High (Compliance & Security) | Process procedural gap | Implement automated technical safeguard to enforce control CTRL-016 | Engineering Lead 16 | Software Engineering | 2026-08-02 | 2026-09-02 | Closed | Medium | Evidence File EVID-016 | EVID-016 Attached | Passed | 22 | No
REM-017 | FIND-017 | Remediate Security Control Deficiency for CTRL-017 | Internal Audit / Vendor Incident | RISK-017 | CTRL-017 | APP-001 | None | Medium | Moderate | High (Compliance & Security) | Process procedural gap | Implement automated technical safeguard to enforce control CTRL-017 | Engineering Lead 17 | Software Engineering | 2026-08-02 | 2026-09-02 | Closed | Medium | Evidence File EVID-017 | EVID-017 Attached | Passed | 22 | No
REM-018 | FIND-018 | Remediate Security Control Deficiency for CTRL-018 | Internal Audit / Vendor Incident | RISK-018 | CTRL-018 | APP-001 | None | Medium | Moderate | High (Compliance & Security) | Process procedural gap | Implement automated technical safeguard to enforce control CTRL-018 | Engineering Lead 18 | Software Engineering | 2026-08-02 | 2026-09-02 | Closed | Medium | Evidence File EVID-018 | EVID-018 Attached | Passed | 22 | No
REM-019 | FIND-019 | Remediate Operational Audit Finding for CTRL-019 | Internal Audit / Vendor Incident | RISK-019 | CTRL-019 | APP-001 | None | Medium | Moderate | High (Compliance & Security) | Process procedural gap | Update procedural documentation and execute evidence collection for CTRL-019 | Operations Lead 19 | IT Operations | 2026-08-02 | 2026-09-02 | In Progress | Medium | Evidence File EVID-019 | EVID-019 Attached | Pending Retest | 14 | No
REM-020 | FIND-020 | Remediate Operational Audit Finding for CTRL-020 | Internal Audit / Vendor Incident | RISK-020 | CTRL-020 | APP-001 | None | Medium | Moderate | High (Compliance & Security) | Process procedural gap | Update procedural documentation and execute evidence collection for CTRL-020 | Operations Lead 20 | IT Operations | 2026-08-02 | 2026-09-02 | In Progress | Medium | Evidence File EVID-020 | EVID-020 Attached | Pending Retest | 14 | No
REM-021 | FIND-021 | Remediate Operational Audit Finding for CTRL-021 | Internal Audit / Vendor Incident | RISK-021 | CTRL-021 | APP-001 | None | Medium | Moderate | High (Compliance & Security) | Process procedural gap | Update procedural documentation and execute evidence collection for CTRL-021 | Operations Lead 21 | IT Operations | 2026-08-02 | 2026-09-02 | In Progress | Medium | Evidence File EVID-021 | EVID-021 Attached | Pending Retest | 14 | No
REM-022 | FIND-022 | Remediate Operational Audit Finding for CTRL-022 | Internal Audit / Vendor Incident | RISK-022 | CTRL-022 | APP-001 | None | Medium | Moderate | High (Compliance & Security) | Process procedural gap | Update procedural documentation and execute evidence collection for CTRL-022 | Operations Lead 22 | IT Operations | 2026-08-02 | 2026-09-02 | In Progress | Medium | Evidence File EVID-022 | EVID-022 Attached | Pending Retest | 14 | No
REM-023 | AUD-023 | Remediate Operational Audit Finding for CTRL-023 | Internal Audit / Vendor Incident | RISK-023 | CTRL-023 | APP-001 | None | Medium | Moderate | High (Compliance & Security) | Process procedural gap | Update procedural documentation and execute evidence collection for CTRL-023 | Operations Lead 23 | IT Operations | 2026-08-02 | 2026-09-02 | In Progress | Medium | Evidence File EVID-023 | EVID-023 Attached | Pending Retest | 14 | No
REM-024 | AUD-024 | Remediate Operational Audit Finding for CTRL-024 | Internal Audit / Vendor Incident | RISK-024 | CTRL-024 | APP-001 | None | Medium | Moderate | High (Compliance & Security) | Process procedural gap | Update procedural documentation and execute evidence collection for CTRL-024 | Operations Lead 24 | IT Operations | 2026-08-02 | 2026-09-02 | In Progress | Medium | Evidence File EVID-024 | EVID-024 Attached | Pending Retest | 14 | No
REM-025 | AUD-025 | Remediate Operational Audit Finding for CTRL-025 | Internal Audit / Vendor Incident | RISK-025 | CTRL-025 | APP-001 | None | Medium | Moderate | High (Compliance & Security) | Process procedural gap | Update procedural documentation and execute evidence collection for CTRL-025 | Operations Lead 25 | IT Operations | 2026-08-02 | 2026-09-02 | In Progress | Medium | Evidence File EVID-025 | EVID-025 Attached | Pending Retest | 14 | No
REM-026 | AUD-026 | Remediate Operational Audit Finding for CTRL-026 | Internal Audit / Vendor Incident | RISK-026 | CTRL-026 | APP-001 | None | Low | Moderate | High (Compliance & Security) | Process procedural gap | Update procedural documentation and execute evidence collection for CTRL-026 | Operations Lead 26 | IT Operations | 2026-08-02 | 2026-09-02 | In Progress | Medium | Evidence File EVID-026 | EVID-026 Attached | Pending Retest | 14 | No
REM-027 | AUD-027 | Remediate Operational Audit Finding for CTRL-027 | Internal Audit / Vendor Incident | RISK-027 | CTRL-027 | APP-001 | None | Low | Moderate | High (Compliance & Security) | Process procedural gap | Update procedural documentation and execute evidence collection for CTRL-027 | Operations Lead 27 | IT Operations | 2026-08-02 | 2026-09-02 | In Progress | Medium | Evidence File EVID-027 | EVID-027 Attached | Pending Retest | 14 | No
REM-028 | AUD-028 | Remediate Operational Audit Finding for CTRL-028 | Internal Audit / Vendor Incident | RISK-028 | CTRL-028 | APP-001 | None | Low | Moderate | High (Compliance & Security) | Process procedural gap | Update procedural documentation and execute evidence collection for CTRL-028 | Operations Lead 28 | IT Operations | 2026-08-02 | 2026-09-02 | In Progress | Medium | Evidence File EVID-028 | EVID-028 Attached | Pending Retest | 14 | No
REM-029 | AUD-029 | Remediate Operational Audit Finding for CTRL-029 | Internal Audit / Vendor Incident | RISK-029 | CTRL-029 | APP-001 | None | Low | Moderate | High (Compliance & Security) | Process procedural gap | Update procedural documentation and execute evidence collection for CTRL-029 | Operations Lead 29 | IT Operations | 2026-08-02 | 2026-09-02 | In Progress | Medium | Evidence File EVID-029 | EVID-029 Attached | Pending Retest | 14 | No
REM-030 | AUD-030 | Remediate Operational Audit Finding for CTRL-030 | Internal Audit / Vendor Incident | RISK-030 | CTRL-030 | APP-001 | None | Low | Moderate | High (Compliance & Security) | Process procedural gap | Update procedural documentation and execute evidence collection for CTRL-030 | Operations Lead 30 | IT Operations | 2026-08-02 | 2026-09-02 | In Progress | Medium | Evidence File EVID-030 | EVID-030 Attached | Pending Retest | 14 | No
REM-031 | AUD-031 | Remediate Operational Audit Finding for CTRL-031 | Internal Audit / Vendor Incident | RISK-031 | CTRL-031 | APP-001 | None | Low | Moderate | High (Compliance & Security) | Process procedural gap | Update procedural documentation and execute evidence collection for CTRL-031 | Operations Lead 31 | IT Operations | 2026-08-02 | 2026-09-02 | In Progress | Medium | Evidence File EVID-031 | EVID-031 Attached | Pending Retest | 14 | No
REM-032 | AUD-032 | Remediate Operational Audit Finding for CTRL-032 | Internal Audit / Vendor Incident | RISK-032 | CTRL-032 | APP-001 | None | Low | Moderate | High (Compliance & Security) | Process procedural gap | Update procedural documentation and execute evidence collection for CTRL-032 | Operations Lead 32 | IT Operations | 2026-08-02 | 2026-09-02 | In Progress | Medium | Evidence File EVID-032 | EVID-032 Attached | Pending Retest | 14 | No