## Sheet
Finding ID | Audit Area | Criteria (Standard/Policy) | Condition (Deficiency Found) | Root Cause | Consequence / Risk Exposure | Privacy Impact | Severity | Recommendation | Management Response | Remediation Owner | Target Due Date | Status | Evidence Reviewed | Retest Result | Closure Date
FIND-001 | Cloud & Application Security | ISO 27001 / HIPAA Standard Clause 1.1 | Procedural audit exception identified in control CTRL-001 execution. | Manual process lack of automated alert trigger. | Moderate residual risk exposure associated with RISK-001. | Moderate | High | Automate control testing and update operational evidence collection for CTRL-001. | Management concurs with finding; remediation action plan assigned. | Technical Lead 1 | 2026-09-15 | Closed | Evidence Log EVID-001 | Passed | 2026-08-10
FIND-002 | Cloud & Application Security | ISO 27001 / HIPAA Standard Clause 2.1 | Procedural audit exception identified in control CTRL-002 execution. | Manual process lack of automated alert trigger. | Moderate residual risk exposure associated with RISK-002. | Moderate | High | Automate control testing and update operational evidence collection for CTRL-002. | Management concurs with finding; remediation action plan assigned. | Technical Lead 2 | 2026-09-15 | Closed | Evidence Log EVID-002 | Passed | 2026-08-10
FIND-003 | Cloud & Application Security | ISO 27001 / HIPAA Standard Clause 3.1 | Procedural audit exception identified in control CTRL-003 execution. | Manual process lack of automated alert trigger. | Moderate residual risk exposure associated with RISK-003. | Moderate | High | Automate control testing and update operational evidence collection for CTRL-003. | Management concurs with finding; remediation action plan assigned. | Technical Lead 3 | 2026-09-15 | Closed | Evidence Log EVID-003 | Passed | 2026-08-10
FIND-004 | Cloud & Application Security | ISO 27001 / HIPAA Standard Clause 4.1 | Procedural audit exception identified in control CTRL-004 execution. | Manual process lack of automated alert trigger. | Moderate residual risk exposure associated with RISK-004. | Moderate | High | Automate control testing and update operational evidence collection for CTRL-004. | Management concurs with finding; remediation action plan assigned. | Technical Lead 4 | 2026-09-15 | Closed | Evidence Log EVID-004 | Passed | 2026-08-10
FIND-005 | Cloud & Application Security | ISO 27001 / HIPAA Standard Clause 5.1 | Procedural audit exception identified in control CTRL-005 execution. | Manual process lack of automated alert trigger. | Moderate residual risk exposure associated with RISK-005. | Moderate | Medium | Automate control testing and update operational evidence collection for CTRL-005. | Management concurs with finding; remediation action plan assigned. | Technical Lead 5 | 2026-09-15 | Closed | Evidence Log EVID-005 | Passed | 2026-08-10
FIND-006 | Cloud & Application Security | ISO 27001 / HIPAA Standard Clause 6.1 | Procedural audit exception identified in control CTRL-006 execution. | Manual process lack of automated alert trigger. | Moderate residual risk exposure associated with RISK-006. | Moderate | Medium | Automate control testing and update operational evidence collection for CTRL-006. | Management concurs with finding; remediation action plan assigned. | Technical Lead 6 | 2026-09-15 | Closed | Evidence Log EVID-006 | Passed | 2026-08-10
FIND-007 | Cloud & Application Security | ISO 27001 / HIPAA Standard Clause 7.1 | Procedural audit exception identified in control CTRL-007 execution. | Manual process lack of automated alert trigger. | Moderate residual risk exposure associated with RISK-007. | Moderate | Medium | Automate control testing and update operational evidence collection for CTRL-007. | Management concurs with finding; remediation action plan assigned. | Technical Lead 7 | 2026-09-15 | Closed | Evidence Log EVID-007 | Passed | 2026-08-10
FIND-008 | Vendor Risk Management | HIPAA BAA Contract & Control CTRL-056 (Vendor Access) | Vendor MedReport Cloud Services (VEND-001) suffered an administrative credential breach due to lack of MFA on maintenance portal. | Vendor failed to enforce multi-factor authentication on legacy local contractor accounts. | Exposure of ~14,200 patient radiology reports (RISK-015 - Score 20 Critical). | High (Patient DICOM Reports Potentially Exposed) | Critical | Mandate Okta SAML SSO federation with FIDO2 WebAuthn MFA and IP whitelisting for VEND-001. | Management agrees; DevOps and Identity team deployed Okta SSO federation on August 15, 2026. | Identity Lead / DevOps Lead | 2026-08-25 | Closed | Evidence Log EVID-015 (Okta SSO Export) | Passed (TEST-015) | 2026-08-20
FIND-009 | Cloud & Application Security | ISO 27001 / HIPAA Standard Clause 9.1 | Procedural audit exception identified in control CTRL-009 execution. | Manual process lack of automated alert trigger. | Moderate residual risk exposure associated with RISK-009. | Moderate | Medium | Automate control testing and update operational evidence collection for CTRL-009. | Management concurs with finding; remediation action plan assigned. | Technical Lead 9 | 2026-09-15 | Closed | Evidence Log EVID-009 | Passed | 2026-08-10
FIND-010 | Cloud & Application Security | ISO 27001 / HIPAA Standard Clause 10.1 | Procedural audit exception identified in control CTRL-010 execution. | Manual process lack of automated alert trigger. | Moderate residual risk exposure associated with RISK-010. | Moderate | Medium | Automate control testing and update operational evidence collection for CTRL-010. | Management concurs with finding; remediation action plan assigned. | Technical Lead 10 | 2026-09-15 | Closed | Evidence Log EVID-010 | Passed | 2026-08-10
FIND-011 | Privacy & Governance | ISO 27001 / HIPAA Standard Clause 11.1 | Procedural audit exception identified in control CTRL-011 execution. | Manual process lack of automated alert trigger. | Moderate residual risk exposure associated with RISK-011. | Low | Medium | Automate control testing and update operational evidence collection for CTRL-011. | Management concurs with finding; remediation action plan assigned. | Technical Lead 11 | 2026-09-15 | Closed | Evidence Log EVID-011 | Passed | 2026-08-10
FIND-012 | Privacy & Governance | ISO 27001 / HIPAA Standard Clause 12.1 | Procedural audit exception identified in control CTRL-012 execution. | Manual process lack of automated alert trigger. | Moderate residual risk exposure associated with RISK-012. | Low | Medium | Automate control testing and update operational evidence collection for CTRL-012. | Management concurs with finding; remediation action plan assigned. | Technical Lead 12 | 2026-09-15 | Closed | Evidence Log EVID-012 | Passed | 2026-08-10
FIND-013 | Privacy & Governance | ISO 27001 / HIPAA Standard Clause 13.1 | Procedural audit exception identified in control CTRL-013 execution. | Manual process lack of automated alert trigger. | Moderate residual risk exposure associated with RISK-013. | Low | Medium | Automate control testing and update operational evidence collection for CTRL-013. | Management concurs with finding; remediation action plan assigned. | Technical Lead 13 | 2026-09-15 | In Progress | Evidence Log EVID-013 | Pending | N/A
FIND-014 | Privacy & Governance | ISO 27001 / HIPAA Standard Clause 14.1 | Procedural audit exception identified in control CTRL-014 execution. | Manual process lack of automated alert trigger. | Moderate residual risk exposure associated with RISK-014. | Low | Medium | Automate control testing and update operational evidence collection for CTRL-014. | Management concurs with finding; remediation action plan assigned. | Technical Lead 14 | 2026-09-15 | In Progress | Evidence Log EVID-014 | Pending | N/A
FIND-015 | Privacy & Governance | ISO 27001 / HIPAA Standard Clause 15.1 | Procedural audit exception identified in control CTRL-015 execution. | Manual process lack of automated alert trigger. | Moderate residual risk exposure associated with RISK-015. | Low | Medium | Automate control testing and update operational evidence collection for CTRL-015. | Management concurs with finding; remediation action plan assigned. | Technical Lead 15 | 2026-09-15 | In Progress | Evidence Log EVID-015 | Pending | N/A
FIND-016 | Privacy & Governance | ISO 27001 / HIPAA Standard Clause 16.1 | Procedural audit exception identified in control CTRL-016 execution. | Manual process lack of automated alert trigger. | Moderate residual risk exposure associated with RISK-016. | Low | Medium | Automate control testing and update operational evidence collection for CTRL-016. | Management concurs with finding; remediation action plan assigned. | Technical Lead 16 | 2026-09-15 | In Progress | Evidence Log EVID-016 | Pending | N/A
FIND-017 | Privacy & Governance | ISO 27001 / HIPAA Standard Clause 17.1 | Procedural audit exception identified in control CTRL-017 execution. | Manual process lack of automated alert trigger. | Moderate residual risk exposure associated with RISK-017. | Low | Low | Automate control testing and update operational evidence collection for CTRL-017. | Management concurs with finding; remediation action plan assigned. | Technical Lead 17 | 2026-09-15 | In Progress | Evidence Log EVID-017 | Pending | N/A
FIND-018 | Privacy & Governance | ISO 27001 / HIPAA Standard Clause 18.1 | Procedural audit exception identified in control CTRL-018 execution. | Manual process lack of automated alert trigger. | Moderate residual risk exposure associated with RISK-018. | Low | Low | Automate control testing and update operational evidence collection for CTRL-018. | Management concurs with finding; remediation action plan assigned. | Technical Lead 18 | 2026-09-15 | In Progress | Evidence Log EVID-018 | Pending | N/A
FIND-019 | Privacy & Governance | ISO 27001 / HIPAA Standard Clause 19.1 | Procedural audit exception identified in control CTRL-019 execution. | Manual process lack of automated alert trigger. | Moderate residual risk exposure associated with RISK-019. | Low | Low | Automate control testing and update operational evidence collection for CTRL-019. | Management concurs with finding; remediation action plan assigned. | Technical Lead 19 | 2026-09-15 | In Progress | Evidence Log EVID-019 | Pending | N/A
FIND-020 | Privacy & Governance | ISO 27001 / HIPAA Standard Clause 20.1 | Procedural audit exception identified in control CTRL-020 execution. | Manual process lack of automated alert trigger. | Moderate residual risk exposure associated with RISK-020. | Low | Low | Automate control testing and update operational evidence collection for CTRL-020. | Management concurs with finding; remediation action plan assigned. | Technical Lead 20 | 2026-09-15 | In Progress | Evidence Log EVID-020 | Pending | N/A
FIND-021 | Privacy & Governance | ISO 27001 / HIPAA Standard Clause 21.1 | Procedural audit exception identified in control CTRL-021 execution. | Manual process lack of automated alert trigger. | Moderate residual risk exposure associated with RISK-021. | Low | Low | Automate control testing and update operational evidence collection for CTRL-021. | Management concurs with finding; remediation action plan assigned. | Technical Lead 21 | 2026-09-15 | In Progress | Evidence Log EVID-021 | Pending | N/A
FIND-022 | Privacy & Governance | ISO 27001 / HIPAA Standard Clause 22.1 | Procedural audit exception identified in control CTRL-022 execution. | Manual process lack of automated alert trigger. | Moderate residual risk exposure associated with RISK-022. | Low | Low | Automate control testing and update operational evidence collection for CTRL-022. | Management concurs with finding; remediation action plan assigned. | Technical Lead 22 | 2026-09-15 | In Progress | Evidence Log EVID-022 | Pending | N/A